## Sheet1
ID | User Story / Task | Priority | Estimation (Story Points) | Status
PBI-101 | As a user, I want to sign up with my email so that I can create an account. | High | 5 | To Do
PBI-102 | As a user, I want to log in securely using JWT authentication. | High | 8 | In Progress
PBI-103 | As an admin, I need a dashboard to manage users. | Medium | 13 | To Do
PBI-104 | As a user, I want to reset my password via email. | High | 5 | Done
PBI-105 | As a developer, I want unit tests for authentication features. | Medium | 8 | In Progress
PBI-106 | As a user, I want a mobile-responsive UI for better experience. | Low | 13 | To Do
PBI-107 | As a QA engineer, I want automated UI tests to prevent bugs. | Medium | 8 | To Do